## Feature Stories
Story ID | Area | Feature | User Story | Expected Behavior | Code Evidence | API / Runtime Evidence | Primary Data | Feature Status | Test Status | Test Method | Last Tested | Errors / Observations | Fix Status | Priority
PT-001 | Shell / Navigation | Brand header and route navigation | As a user, I can move between the core Pillar Time work areas from the header without losing app state. | Header shows Pillar Time lockup, nav buttons route by hash, active route is highlighted, source/lens counts update from state. | src/main.jsx Shell, routeFromHash, App | /api/state | route hash + app state | Code inventoried | Partial passed | Manual UI route smoke | 2026-06-22 | Browser smoke: app shell loads; route navigation still needs full click-through across nav buttons. | Open | P1
PT-002 | Shell / Updates | Desktop update status and install controls | As a desktop user, I can see when a signed update is available and install or restart from Help/Settings. | Desktop-only update state is checked on startup; Help menu and banner show current/available/installed/error states; install and restart buttons call Tauri updater APIs. | src/main.jsx useDesktopUpdates, Shell, Settings; src/desktopRuntime.js | Tauri updater plugin | desktop updater metadata | Implemented with desktop update view-state guardrails | Unit partial passed | node --test tests/desktopUpdates.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover silent startup checks, current/available/error result states, install start/progress/installed/error states, Help menu message/icon, banner visibility, busy controls, and Settings labels/notices. Packaged desktop updater, real release check, install, and relaunch behavior pending. | Desktop update guardrails covered; packaged Tauri updater smoke pending. | P2
PT-003 | Onboarding | Welcome and executive profile | As a first-time user, I can enter my name and operating manual so briefs are personalized without hard-coded Paul-specific content. | Onboarding requires a non-default first name, saves ownerName, audienceContext, voiceRules, and time operatingManual; profile step advances only after save. | src/main.jsx Onboarding saveExecutiveProfile | PATCH /api/brief-config; PATCH /api/time/preferences | brief_config, time_preferences | Code inventoried | Partial passed | Manual onboarding fresh profile | 2026-06-22 | Browser smoke: first name entered during onboarding without crash; full onboarding path still needs complete end-to-end test. | Open | P0
PT-004 | Onboarding | Starter commitment capture | As a user, I can add one initial commitment during onboarding so Today has immediate planning context. | Submitting starter commitment creates both a time task and daily commitment, shows success, refreshes state, and clears input. | src/main.jsx Onboarding addStarterCommitment | POST /api/time/tasks; POST /api/time/commitments | time_tasks, daily_commitments | Implemented with starter commitment guardrails | Unit partial passed | node --test tests/starterCommitment.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover blank validation, trimmed title, task + daily commitment creation, rank cap at 3, success tone, refresh after persistence, and failure preserving input. Browser onboarding smoke still pending. | Starter commitment guardrails covered; browser onboarding smoke pending. | P1
PT-005 | Onboarding | Reminder defaults setup | As a user, I can choose default reminder gates during onboarding without enabling surprise delivery. | Reminder master/channel defaults save to time preferences; reminders remain controlled by explicit switches. | src/main.jsx Onboarding saveReminderDefaults; Reminders | PATCH /api/time/preferences | time_preferences | Implemented with reminder default guardrails | Unit partial passed | node --test tests/reminderDefaults.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover master/regular/sporadic gate patches, channel merge patches, save route to /api/time/preferences, invalid keys, persistence errors, and no individual reminder enablement from channel defaults. Browser onboarding switch smoke still pending. | Reminder default guardrails covered; browser onboarding smoke pending. | P1
PT-006 | Onboarding | Review template setup | As a user, I can enable or disable review templates during onboarding. | Review template toggle updates enabled state and shows confirmation; disabled templates do not schedule prompts. | src/main.jsx Onboarding toggleReview; Reviews | PATCH /api/time/reviews/:id | review_templates | Implemented with review template guardrails | Unit partial passed | node --test tests/reviewTemplates.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover enable/disable request payloads, required review id, success/warning messages, persistence errors, and payload shape limited to template enabled state so it does not schedule prompt/reminder fields directly. Browser onboarding switch smoke still pending. | Review template guardrails covered; browser onboarding smoke pending. | P2
PT-007 | Onboarding | Model provider setup | As a user, I can save an AI provider key, detect models, and continue even if I defer model setup. | Model step supports provider selection, key paste, model discovery, manual model entry, save, and clear error messages. | src/main.jsx Onboarding detectModels/saveModel; Settings model modal | POST /api/model/models; PATCH /api/model | model_settings, connector credentials | Code inventoried; model provider validation and discovery parsing covered by unit tests | Unit partial passed | node:test fixture for provider normalization, credential readiness, save validation, model list parsing, runtime URLs; live provider/modal still needed | 2026-06-22 | Unit coverage confirms unsupported provider fallback, OpenAI/xAI defaults, saved/env/missing credential statuses, custom Base URL requirement, no API key exposure in settings view, provider runtime base URLs, and Gemini/OpenAI-compatible model discovery parsing. Fixed bug where empty model records could show as literal "undefined". UI modal and live bad-key/provider discovery remain untested. | Open | P0
PT-008 | Onboarding | Brief intent drafting | As a user, I can describe what the daily operating brief should optimize for and get a starter config. | Brief setup draft uses model when available and local fallback on 404/model failure; user can edit sections and apply draft. | src/main.jsx Onboarding generateBriefSetupDraft/applyBriefSetupDraft; server sanitizeBriefSetupDraft | POST /api/onboarding/brief-setup-draft; POST /api/onboarding/brief-setup-apply | brief_config, onboarding state | Implemented with brief setup draft fallback guardrails | Unit partial passed | node --test tests/briefSetupDraft.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover local starter draft preservation of owner/topics/preferences, calendar section ordering, draft/apply request payloads, local fallback for route/model/provider/key failures, and compatible apply fallback writes. UI now falls back locally for model/key/provider errors instead of only 404. Browser onboarding edit/apply smoke still pending. | Brief setup draft guardrails covered; browser onboarding smoke pending. | P1
PT-009 | Onboarding | Source suggestions | As a user, I can get source suggestions from intent and selectively add only ready sources. | Suggestions display loading progress/counts, selected set, blocked prerequisites, skip behavior, and save chosen sources. | src/main.jsx Onboarding suggestSources; server source suggestion helpers | POST /api/onboarding/source-suggestions; POST /api/sources | sources, onboarding state | Implemented with source suggestion selection guardrails | Unit partial passed | node --test tests/sourceSuggestions.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover gated prerequisites for X/Calendar/Podcast transcription, selected-set decisions, blocked-source access routing, empty selection messaging, continue-after-access guard, skip behavior, and /api/sources create payloads. Browser visual/progress-count smoke still pending. | Source suggestion guardrails covered; browser onboarding smoke pending. | P1
PT-010 | Onboarding | Calendar setup | As a user, I can connect Google Calendar during onboarding and return to the app. | Calendar flow opens OAuth in external browser, handles callback, saves refresh token, discovers calendars, and returns to app. | src/main.jsx Onboarding calendar step; server google calendar OAuth handlers | POST /api/google-calendar/oauth/start; GET /api/google-calendar/oauth/callback | connector_credentials.google_calendar | Implemented with onboarding flow guardrails | Unit partial passed | node --test tests/calendarOnboarding.test.js plus full npm test; npm run build | 2026-06-22 | Extracted and tested onboarding calendar click-flow logic: OAuth start calls the server, refreshes state, opens the returned external auth URL, refresh status calls calendars when connected or test when not connected, and success/warning message tone is deterministic. Live Google consent callback, Chrome handoff, and visual onboarding browser smoke remain pending. | Onboarding flow guardrails covered; live OAuth/browser smoke pending | P0
PT-011 | Onboarding | Telegram setup | As a user, I can pair Telegram delivery during setup. | Bot token validates, pairing session/QR can start, polling records chat ID, and state reflects connection. | src/main.jsx TelegramPairingFlow/Onboarding; server Telegram pairing routes | POST /api/telegram/token/validate; POST /api/telegram/pairing/start | telegram_settings | Implemented with Telegram pairing guardrails | Unit partial passed | node --test tests/telegramPairing.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover token validation/start request order, pairing poll request, paired-state detection from session or saved settings, waiting/failed/connected status view, and success/warning message tone. Live Telegram Bot API pairing smoke still pending. | Telegram pairing guardrails covered; live Telegram smoke pending. | P1
PT-012 | Onboarding | Schedule and completion gate | As a user, I can set delivery schedule/timezone and complete onboarding only when minimum required setup is done. | Completion requires ownerName and scheduleSet; completion stores current step complete and returns to app. | src/main.jsx Onboarding readiness/canComplete | PATCH /api/brief-config; POST /api/onboarding/complete | onboarding_state, brief_config | Implemented with onboarding completion guardrails | Unit partial passed | node --test tests/onboardingCompletion.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover non-default owner requirement, schedule requirement, first incomplete routing, reopening completed onboarding at missing required steps, delivery schedule patch payload, and completion endpoint request. Server /api/onboarding/complete also enforces canComplete. Browser completion smoke still pending. | Schedule/completion gate guardrails covered; browser onboarding smoke pending. | P1
PT-013 | Today | Generate executive day brief | As a user, I can generate a day brief centered on schedule, commitments, Linear, and approvals. | Generate button starts executive_day workflow by default; progress updates; result saved and displayed in Briefs. | src/main.jsx Today/Briefs runWorkflow; server executeWorkflow/executeExecutiveDayWorkflow | POST /api/workflow-runs; POST /api/day-briefs | workflow_runs artifact | Code inventoried | Partial passed | Manual run with model missing and model ready | 2026-06-22 | Browser smoke: Today route renders post-onboarding; generation behavior still needs workflow test. API integration: executive day workflow completed; UI Generate button still needs click-through. | Open | P0
PT-014 | Today | Highest leverage suggestions | As a user, I can see ranked suggestions with reasons, category, source, score, and estimate. | Suggestions are ranked by leverage/time engine; cards show score/category/source/estimate and allow accept/not today/incorrect. | src/main.jsx TimeSuggestionCard; server timeSuggestions/rankActions | POST /api/time/commitments; POST /api/time/suggestions/:id/feedback | time_suggestions, suggestion_feedback | Code inventoried | Partial passed | Unit rankActions + manual UI | 2026-06-22 | Automated unit coverage for rankActions passed; UI accept/feedback still needs manual/browser test. API integration: suggestion feedback endpoint accepted; ranking UI still partially covered. | Open | P1
PT-015 | Today | Today’s Three commitments | As a user, I can accept, complete, or remove the commitments Pillar Time should protect today. | Accepted suggestions create daily commitments; done/remove patch status; Today metric updates active commitments. | src/main.jsx Today, TimeSuggestionCard; server dailyCommitments routes | POST/PATCH /api/time/commitments | daily_commitments | Code inventoried | Passed | Manual commit lifecycle | 2026-06-22 | API integration: commitment create/done patch accepted. | Open | P0
PT-016 | Today | Quick task capture | As a user, I can quickly capture a task from Today without opening Planner. | Submitting non-empty quick capture creates an inbox task with source quick-capture and clears input. | src/main.jsx Today addTask | POST /api/time/tasks | time_tasks | Implemented with quick task capture guardrails | Unit partial passed | node --test tests/quickTaskCapture.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover blank prevention, title trimming, POST /api/time/tasks payload with source quick-capture, successful clear, and persistence-failure input preservation. Browser Today form smoke pending. | Quick capture guardrails covered; browser Today smoke pending. | P1
PT-017 | Today | Agenda timeline from latest brief | As a user, I can see recent calendar agenda context on Today. | Today pulls calendarAgenda from latest completed run, shows up to 8 events, and opens calendar URL when present. | src/main.jsx latestCalendarAgenda, Today | workflow artifact only | workflow_runs artifact.calendarAgenda | Implemented with agenda timeline helper guardrails | Unit partial passed | node --test tests/todayAgenda.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover latest completed workflow artifact selection, legacy calendarFetch fallback, eight-event cap, row label/time fallback, and calendarUrl preservation for Open action. Browser Today timeline smoke pending. | Agenda timeline guardrails covered; browser Today timeline smoke pending. | P1
PT-018 | Today | Next reminders preview | As a user, I can see upcoming reminders and jump to edit them. | Today lists first reminders with next occurrence, on/off badge, and edit route action. | src/main.jsx Today reminders list | /api/state | reminders | Implemented with Today reminder preview guardrails | Unit partial passed | node --test tests/todayReminders.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover first-six reminder cap, next occurrence text, On/Off badge tone/copy, reminders route edit action, no-next-occurrence fallback, missing id/title fallback, and existing local time display style. Browser visual smoke against live /api/state pending. | Today reminder preview guardrails covered; browser route smoke pending. | P2
PT-019 | Planner | Task creation | As a user, I can create a rankable task with notes, leverage category, estimate, and priority. | Planner form validates title, posts task, resets form, and new task appears in backlog. | src/main.jsx Planner createTask; server /api/time/tasks | POST /api/time/tasks | time_tasks | Code inventoried | Passed | Manual task create | 2026-06-22 | Browser smoke: Planner route renders; task creation persisted to backlog. API integration: task create/done accepted; browser task create persisted to backlog. | Open | P1
PT-020 | Planner | Task backlog lifecycle | As a user, I can mark tasks done or archive them from the backlog. | Backlog buttons patch status to done/archive; completed_at set for done; list refreshes. | src/main.jsx Planner backlog; server patch task | PATCH /api/time/tasks/:id | time_tasks | Code inventoried | Passed | Manual done/archive | 2026-06-22 | API integration: task lifecycle done patch accepted. | Open | P1
PT-021 | Planner | Important dates | As a user, I can save important dates that should influence planning. | Important date requires title/date, saves category/notes/default enabled, and displays in Planner. | src/main.jsx Planner createDate; server /api/time/important-dates | POST /api/time/important-dates | important_dates | Code inventoried | Passed | Manual date create + missing date validation | 2026-06-22 | Browser smoke: important date creation persisted to list. API integration and browser smoke: validation/create accepted and list updated. | Open | P2
PT-022 | Reminders | Global reminder gates | As a user, I can control master, regular, sporadic, and channel reminder settings. | Settings persist to time preferences; disabled master prevents surprise delivery; channel toggles update nested channels. | src/main.jsx Reminders; server /api/time/preferences | PATCH /api/time/preferences | time_preferences | Code inventoried | Passed | Manual toggle persistence | 2026-06-22 | Browser smoke: Reminders route renders; visible master switch toggles state. API integration: time preferences patch accepted; browser switch row toggled state. | Open | P0
PT-023 | Reminders | Create reminder | As a user, I can create regular/sporadic/review reminders and choose schedule/time/channels. | Create form requires title, defaults disabled, saves schedule metadata and next occurrence appears. | src/main.jsx Reminders createReminder; server /api/time/reminders | POST /api/time/reminders | reminders | Code inventoried | Passed | Manual create all schedule types | 2026-06-22 | API integration: reminder create accepted. | Open | P1
PT-024 | Reminders | Reminder enable pause archive | As a user, I can enable/disable, pause, or archive a reminder. | Reminder list buttons patch enabled/pausedUntil/archive; archived reminders should disappear from active list. | src/main.jsx Reminders list; server patch reminder | PATCH /api/time/reminders/:id | reminders | Code inventoried | Passed | Manual enable/pause/archive | 2026-06-22 | API integration: reminder enable/archive accepted. | Open | P1
PT-025 | Reminders | Scheduler delivery | As a user, enabled reminders should deliver through enabled channels at the right local time. | Scheduler tick respects master switch, reminder enabled state, paused/archived state, next occurrence, dedupe, quiet/catchup, and records attempts. | server runTimeReminderSchedulerTick/deliverTimeReminder | internal scheduler; Telegram/local notifications | reminder_attempts | Code inventoried; scheduler decision logic covered by unit tests | Unit partial passed | node:test fixture for master/type gates, pause, dedupe, local due time, and channel plans; live Telegram/manual delivery still needed | 2026-06-22 | Unit coverage confirms scheduler skips when master/reminder/type gates are off, respects pause and skipped dedupe keys, schedules not-yet-due occurrences without delivery, detects local due time, plans Telegram sends only when both reminder/global channels are enabled, and records desktop text as skipped pending Tauri notification wiring. Live Telegram delivery and persisted attempt rows remain untested. | Open | P0
PT-026 | Reviews | Review templates | As a user, I can enable review templates and read their prompts. | Review page renders seeded templates, cadence/description/prompts, and enable/disable persists. | src/main.jsx Reviews; server seedTimeDefaults | PATCH /api/time/reviews/:id | review_templates | Code inventoried | Passed | Manual review toggle | 2026-06-22 | Browser smoke: Reviews route renders. API integration: review toggle accepted; browser route rendered. | Open | P2
PT-027 | Meetings | Meeting records | As a user, I can capture prep notes or after-action notes for meetings. | Meeting form requires title, stores notes/start/objective/action fields where available, and displays saved records. | src/main.jsx Meetings; server /api/time/meetings | POST /api/time/meetings | meeting_records | Code inventoried | Passed | Manual meeting create | 2026-06-22 | Browser smoke: Meetings route renders. API integration: meeting validation/create accepted; browser route rendered. | Open | P1
PT-028 | Trusted Context | Envelope preview | As a user, I can preview what context Pillar Time would use for a task and mode. | Preview form posts explicit mode/partition/task/externalVisibility and renders envelope JSON + quality warnings. | src/main.jsx TrustedContext; server createTrustedContextEnvelope | POST /api/trusted-context/envelope-preview | profile_facts, context constitution | Code inventoried | Passed | Unit trustedContext + manual preview | 2026-06-22 | Automated trusted context envelope/freshness/disclosure tests passed; UI preview still needs manual/browser test. Browser smoke: Trusted Context route renders; unit envelope tests pass. API integration: fact create and envelope preview accepted; unit trusted-context tests passed. | Open | P0
PT-029 | Trusted Context | Add profile facts | As a user, I can add verified or unverified profile facts with partition, visibility, trust, and verification status. | Fact form validates fieldKey, saves fact, audits action, clears value, and fact appears in table. | src/main.jsx TrustedContext saveFact; server /api/trusted-context/facts | POST /api/trusted-context/facts | profile_facts, audit_logs | Code inventoried; profile fact validation and hydration covered by unit tests | Unit partial passed | node:test fixture for profileFactInput/profileFactFromRow; browser form still needed | 2026-06-22 | Unit coverage confirms fieldKey is required, invalid partition/visibility/trust default safely, verified canonical facts default to verified, confidence is clamped, allowed audiences and fieldAuthorityRank are stored in value metadata, and malformed value_json does not break row hydration. Browser fact form save/clear/table refresh remains untested. | Open | P0
PT-030 | Trusted Context | Memory proposal approval | As a user, I can approve or reject learned memory proposals before they become trusted context. | Proposal list displays proposed value/confidence/status; approve/reject patches status and approved proposals create/update facts. | src/main.jsx TrustedContext updateProposal; server proposals routes | PATCH /api/trusted-context/proposals/:id | memory_proposals, profile_facts | Code inventoried | Passed | Unit proposeProfileUpdate + manual approve | 2026-06-22 | Automated proposal behavior test passed; UI approve/reject still needs manual/browser test. API integration: proposal create/approve accepted; unit proposal test passed. | Open | P0
PT-031 | Trusted Context | Workspace constitution | As a user, I can inspect and update the context constitution that governs disclosure and trust. | Current constitution renders; backend can version updates with editor/reason and audit them. | src/main.jsx TrustedContext; server /api/trusted-context/constitution | POST /api/trusted-context/constitution | context_constitution_versions | Implemented with constitution view and versioning guardrails | Unit partial passed | node --test tests/constitutionVersioning.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover current constitution version/body rendering, version increment, body fallback, editor/reason normalization, and audit metadata. Browser Trusted Context panel smoke and DB route integration smoke pending. | Workspace constitution guardrails covered; browser and live DB route smoke pending. | P1
PT-032 | Sources | Source table search and status toggles | As a user, I can find, pause, resume, edit, or delete any configured source. | Sources page filters by name/type/locator, active toggle patches status, edit opens modal, delete removes source. | src/main.jsx Sources; server source routes | PATCH/DELETE /api/sources/:id | sources | Code inventoried | Passed | Manual source CRUD | 2026-06-22 | Browser smoke: Sources route renders and Add source modal opens. API integration: source create/update/delete accepted; browser Add source modal opened. | Open | P0
PT-033 | Sources | Add RSS feed source | As a user, I can add RSS/news feed sources for intelligence mode. | RSS modal collects feed URL/keywords as required, saves locator/config, and fetcher parses feed items. | src/main.jsx Sources sourceDefinitions; server fetchRssSource | POST /api/sources; workflow fetch | sources, normalized_items | Implemented with RSS source form and feed parsing guardrails | Unit partial passed | node --test tests/rssSource.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover RSS modal feed URL/keywords contract, add/edit source payload locator/config, conditional RSS fetch headers, missing-feed skip, RSS/Atom parsing, today filtering, fetch counts, and cache validator config updates. Browser add-source smoke and live RSS fetch smoke pending. | RSS source guardrails covered; browser source modal and live feed smoke pending. | P1
PT-034 | Sources | Add web source | As a user, I can add a web URL/search source. | Web source saves URL/query config and fetcher inserts fetched text or reports fetch errors. | src/main.jsx Sources; server fetchWebSource | POST /api/sources; workflow fetch | sources, normalized_items | Implemented with web source fetch guardrails | Unit partial passed | node --test tests/webSource.test.js; npm test; npm run build | 2026-06-22 | Helpers cover Web source form save/edit payloads, request headers/cache validators, metadata extraction, normalized insertion payload, next config, and error config; no live public URL workflow fetch. | No open fix from unit pass | P2
PT-035 | Sources | Add X search source | As a user, I can add X search sources with constrained quick mode. | X sources require bearer token connector; quick search caps posts, excludes replies/retweets, caches, and reports cost/diagnostics. | src/main.jsx Sources/Settings X; server fetchXSource | PATCH /api/connectors/x; fetch X API | sources, connector_credentials | Implemented with X quick-search guardrails | Unit partial passed | node --test tests/xSource.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover missing query/token skips, quick query reply/retweet exclusions, locked max_results cap, today filtering, post normalization, rising-score engagement math, estimated cost, and quick-mode config diagnostics. Live X API smoke and source modal browser smoke pending. | X quick-search guardrails covered; live API and browser source-modal smoke pending. | P1
PT-036 | Sources | Add Reddit source | As a user, I can add subreddit sources using OAuth when configured. | Reddit connector stores client settings, refreshes access token, fetches subreddit JSON, falls back/diagnoses failures. | src/main.jsx Sources/Settings Reddit; server reddit functions | PATCH /api/connectors/reddit; POST /api/reddit/test | sources, connector_credentials | Implemented with Reddit OAuth/API and fallback guardrails | Unit partial passed | node --test tests/redditSource.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover stored/env credential merge, installed-client and client-credential token request plans, subreddit/user/search URL construction, listing post normalization, 403/429 RSS fallback detection, and fetch-mode config diagnostics. Live Reddit OAuth/API smoke and browser connector/source modal smoke pending. | Reddit connector/fetch guardrails covered; live API and browser connector smoke pending. | P1
PT-037 | Sources | Add YouTube source | As a user, I can add YouTube channel feeds as source input. | YouTube source resolves feed URL/channel config and fetches entries as normalized items when active. | src/main.jsx Sources; server seedDefaultYouTubeSources/fetch RSS path | POST /api/sources | sources, normalized_items | Implemented with YouTube source feed guardrails | Unit partial passed | node --test tests/youtubeSource.test.js; npm test; npm run build | 2026-06-22 | Helpers cover channel/playlist feed URLs, handle page channel ID resolution, Atom parse/today filtering, and next config; no live YouTube network smoke. | No open fix from unit pass | P2
PT-038 | Sources | Add podcast source | As a user, I can add podcast RSS or Spotify source and optionally transcribe new episodes. | Spotify resolver can find RSS; transcription checkbox disabled unless FFmpeg plus local/cloud STT ready; source fetch can transcribe today episodes. | src/main.jsx Sources resolve/transcribe; server podcast functions | POST /api/podcast/resolve-spotify; POST /api/sources/:id/transcribe | sources, documents, normalized_items | Implemented with podcast source and transcription gating guardrails | Unit partial passed | node --test tests/podcastSource.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover Spotify title cleanup/candidates, RSS audio episode parsing, today/latest selection, no-episode config/result, duplicate transcript result, transcription availability gating, and Spotify resolve form patch. Browser source modal, live Spotify/iTunes resolver, and real audio transcription smoke pending. | Podcast source guardrails covered; live resolver/audio and browser source-modal smoke pending. | P1
PT-039 | Sources | Add calendar source | As a user, I can add selected calendar sources without all-day/group calendars blocking my day. | Calendar source requires Google connection; selected calendars fetch agenda; all-day events are context but not blocking busy intervals. | src/main.jsx Sources Calendar; server calendar fetch/planning functions | POST /api/sources; Google Calendar API | sources, connector_credentials, workflow artifact | Code inventoried; backend calendar blocking invariant covered | Unit partial passed | node:test fixture for all-day/context nonblocking; manual Google source selection still needed | 2026-06-22 | Unit coverage confirms all-day events and non-primary/context calendars do not block busy intervals; live OAuth/calendar selection path remains untested. | Open | P0
PT-040 | Perspective Lenses | Manage lenses | As a user, I can create, edit, enable, disable, remove, search, and save deliberation lenses. | Lens edits are local until Save; unsaved message appears; saved lenses persist in brief config and count in nav. | src/main.jsx Lenses | PATCH /api/brief-config | brief_config.perspectiveLenses | Implemented with perspective lens management guardrails | Unit partial passed | node --test tests/perspectiveLenses.test.js; npm test; npm run build | 2026-06-22 | Helpers cover local edit/add/update/remove/filter, unsaved/saved message state, PATCH /api/brief-config payload, and enabled nav count; no live browser click-through. | No open fix from unit pass | P2
PT-041 | Perspective Lenses | Generate lenses from prompt | As a user, I can ask Pillar Time to generate perspective lenses from a prompt. | Prompt posts to backend, generated lenses appear as drafts, failures show message, voice input can fill prompt when STT works. | src/main.jsx Onboarding perspective generation; Lenses | POST /api/perspective-lenses/generate; POST /api/audio/transcribe | brief_config.perspectiveLenses | Implemented with perspective lens generation guardrails | Unit partial passed | node --test tests/perspectiveLensGeneration.test.js; npm test; npm run build | 2026-06-22 | Helpers cover prompt count inference, backend prompt construction, draft sanitation/limits, generation success/failure messages, and voice transcript append/failure; no live model or mic/STT smoke. | No open fix from unit pass | P2
PT-042 | Linear | Linear connector readiness | As a user, I can enable/test Linear using a local environment key without pasting secrets into the app. | Settings shows env-only connector, test hits viewer, errors explain LINEAR_API_KEY missing; no SQLite storage of key. | src/main.jsx Linear/Settings; server linearApiKey/linearPublicConnector | POST /api/linear/test; PATCH /api/connectors/linear | connector_credentials without api key | Code inventoried | Unit partial passed | Unit LinearClient + manual env missing/ready | 2026-06-22 | Automated Linear client auth/missing-key tests passed; live connector UI still needs manual/browser test. | Open | P0
PT-043 | Linear | Linear issue browsing | As a user, I can view assigned/open Linear issues grouped by project with filters. | Linear page bootstraps viewer/teams/projects/states, supports team/assignee/state/project filters, groups issues, and reports API errors. | src/main.jsx Linear; server /api/linear/bootstrap/issues | GET /api/linear/bootstrap; GET /api/linear/issues | Linear API live data | Code inventoried | Partial passed | Manual with LINEAR_API_KEY | 2026-06-22 | Automated Linear pagination/grouping test passed; live issue browser still needs manual/browser test. Browser smoke: Linear route renders without env key; live connector still untested. | Open | P0
PT-044 | Linear | Manual Linear writes | As a user, I can create, update, and comment on Linear issues from the Linear page. | Manual actions require visible user action, validate required fields, call Linear API, audit success/failure, and refresh visible issues. | src/main.jsx Linear forms; server Linear routes | POST/PATCH /api/linear/issues; POST comments | Linear API, audit_logs | Code inventoried | Unit partial passed | Unit client mutations + manual write in test project | 2026-06-22 | Automated Linear create/update/comment request-shape tests passed; live manual writes still need approval-scoped testing. | Open | P0
PT-045 | Brief Setup | Brief configuration editing | As a user, I can configure sections, source recency, analyzer instructions, and delivery shape. | Brief Setup page edits brief_config and should persist sections, lenses/council legacy, delivery frequency/time/day/timezone. | src/main.jsx BriefSetup; server /api/brief-config | PATCH /api/brief-config | brief_config | Code inventoried | Passed | Manual config edit/persist | 2026-06-22 | API integration: brief config patch accepted. | Open | P1
PT-046 | Documents | Trusted/saved documents | As a user, I can save documents or context that future briefs can retrieve. | Documents page creates/patches documents; workflow retrieves saved docs before synthesis. | src/main.jsx Documents; server documents/retrieve step | POST/PATCH /api/documents | documents | Code inventoried | Passed | Manual document CRUD + brief retrieval | 2026-06-22 | API integration: document create/update accepted. | Open | P1
PT-047 | Workflow | Workflow progress display | As a user, I can see each workflow run step and failure reason instead of a frozen app. | Progress screen shows current step, completed/error status, slow-step working state, and exact error text. | src/main.jsx GeneratingBrief/BriefGenerationProgress; server workflow steps | POST /api/workflow-runs; GET /api/workflow-runs/:id | workflow_runs.steps_json/status | Implemented with UX wording fix | Unit partial passed | node --test tests/progressViewModel.test.js plus full npm test; npm run build | 2026-06-22 | Extracted progress-screen view model and verified active/done/error states, exact error text, slow-step working class, progress percentage, and step classes. Fixed duplicate punctuation when an output such as Working... already ends in punctuation. Browser visual smoke of the rendered React screen remains pending. | UX punctuation fixed; browser visual smoke pending | P0
PT-048 | Approvals | Approval queue | As a user, I can review generated actions before they touch external systems. | Approvals page lists proposed actions, can approve/reject via patch, and execute approved supported actions. | src/main.jsx Approvals; server approvals routes | PATCH /api/approvals/:id; POST /api/approvals/:id/execute | approval_items, audit_logs | Code inventoried; queue serialization and approve/reject transition rules covered by unit tests | Unit partial passed | node:test fixture for approval queue serialization/status transitions; browser Approval page still needed | 2026-06-22 | Unit coverage confirms approval queue rows serialize payloads safely, malformed payload JSON does not crash the queue, approve/reject transitions validate status and produce audit metadata, and next pending selection uses oldest pending item or requested pending id. UI review/approve/reject flow remains untested. | Open | P0
PT-049 | Approvals | Approval-gated Linear actions | As a user, generated Linear create/update/comment actions never execute until approved. | Executive workflow creates approval_items; execute endpoint performs Linear action, refetches/verifies when possible, audits result; rejects unsupported action types. | server proposedLinearActionsFromContext/createApprovalItemsForRun/executeApprovalItem | POST /api/approvals/:id/execute | approval_items, Linear API, audit_logs | Code inventoried; approval-gated Linear executor guardrails covered by unit tests | Unit partial passed | node:test fixture with fake Linear client; live Linear execution still needed | 2026-06-22 | Unit coverage confirms pending approvals do not call Linear, approved addComment executes and refetches when requested, update/create payload validation fails before connector calls, and unsupported Linear operations are rejected. Live Linear API execution remains untested. | Open | P0
PT-050 | Briefs | Brief list and reader | As a user, I can search/select saved briefs and read rendered artifact content. | Briefs page lists workflow runs with status/delivery badge, search filters, selected reader renders markdown and diagnostics. | src/main.jsx Briefs/BriefArtifact | GET /api/state; GET /api/workflow-runs/:id | workflow_runs artifact | Code inventoried | Partial passed | Manual list/search/select | 2026-06-22 | Browser smoke: Briefs route renders. | Open | P1
PT-051 | Briefs | Proposed calendar strip | As a user, I can see proposed day schedule tiles at the top of a brief. | Brief artifact renders proposedCalendar as tiles with time/category/title and approval button when pending. | src/main.jsx ProposedCalendarStrip; server proposedCalendarScheduleFromContext | workflow artifact + approvals | approval_items calendar action | Code inventoried; backend proposal block generation covered | Unit partial passed | node:test fixture for proposedCalendarScheduleFromContext; UI strip still needs manual verification | 2026-06-22 | Backend creates proposed schedule blocks from ranked candidates and skips calendar_conflict candidates; rendered tile strip and approve button still need browser/manual test. | Open | P0
PT-052 | Briefs | Approve calendar plan | As a user, I can approve a proposed schedule and have Pillar Time create calendar blocks around existing events. | Calendar approval executes createGoogleCalendarEvent for proposed schedule blocks, skips nonblocking/all-day conflicts, verifies/audits creation. | src/main.jsx ProposedCalendarStrip; server executeApprovalItem/createGoogleCalendarEvent | POST /api/approvals/:id/execute; Google Calendar insert | approval_items, Google Calendar | Code inventoried; calendar schedule approval executor guardrails covered by unit tests | Unit partial passed | node:test fixture with fake Google Calendar executor; live Calendar insert still needed | 2026-06-22 | Unit coverage confirms approved calendar_schedule actions call the Calendar executor with schedule block metadata and pending/empty/unsupported actions fail before connector calls. Live Google Calendar insert and UI approve button remain untested. | Open | P0
PT-053 | Briefs | Add context and regenerate | As a user, I can add typed or voice context when a brief missed something and regenerate the day plan. | Brief reader opens context panel, accepts typed/voice note, starts executive_day run with additionalContext and basedOnRunId, then selects new run. | src/main.jsx Briefs regenerateWithContext/captureVoiceContext; server buildExecutiveDayContext | POST /api/workflow-runs | workflow_runs artifacts | Code inventoried; regeneration context normalization and synthesis payload covered by unit tests | Unit partial passed | node:test fixture for additionalContext/basedOnRunId carry-forward; browser button and voice fallback still needed | 2026-06-22 | Unit coverage confirms added context is trimmed/preserved, basedOnRunId is carried, and synthesis payload includes the live correction plus communication contract. UI regenerate flow and browser voice-note fallback remain untested. | Open | P0
PT-054 | Briefs | Audio brief generation/playback | As a user, I can generate, play, pause, and restart an audio version of a saved brief when TTS is configured. | Audio button disabled until TTS ready; generation stores MP3 URL; playback state follows audio events; restart resets time. | src/main.jsx Briefs audio functions; server synthesize/send audio | POST /api/workflow-runs/:id/audio; GET /api/audio/:fileName | audio files, artifact.audio | Implemented with audio brief generation/playback guardrails | Unit partial passed | node --test tests/briefAudio.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover disabled button state until TTS ready, generate/play/pause/restart labels, selected-run audio reset, audio event state transitions, restart currentTime reset, markdown/link cleanup for TTS payloads, cached MP3 reuse, artifact storage shape, and safe MP3 basename serving. Live ElevenLabs generation/playback and browser audio interaction pending. | Audio brief guardrails covered; live ElevenLabs playback smoke pending. | P1
PT-055 | Briefs | Perspective deliberation | As a user, I can run enabled lenses against a saved brief and see synthesis. | Deliberate button disabled without enabled lenses; backend generates/saves deliberation; regenerate refreshes existing result. | src/main.jsx DeliberationPanel; server deliberateWorkflowRun | POST /api/workflow-runs/:id/deliberate | workflow_runs artifact.deliberation | Code inventoried | Not tested | Manual with enabled lens/model |  |  | Open | P2
PT-056 | Executive Workflow | Build executive day context | As a user, the default brief uses calendar, Linear, tasks, commitments, reminders, meetings, important dates, approvals, trusted context, and connector health. | Executive flow must not use cached news unless intelligence mode requested; context contains calendarAgenda, linearContext, commitments/local, risks, proposed actions, diagnostics. | server buildExecutiveDayContext/executeExecutiveDayWorkflow | POST /api/workflow-runs runType executive_day; POST /api/day-briefs | workflow_runs artifact | Code inventoried | Partial passed | Backend integration with no active sources | 2026-06-22 | API integration: executive artifact created without active news requirement; full artifact contents still need deeper assertion. | Open | P0
PT-057 | Executive Workflow | Deterministic fallback brief | As a user, missing model connector should still produce a useful structured executive brief. | If model is not ready, workflow renders deterministic executive brief instead of stopping at synthesis. | server synthesizeExecutiveDayBrief/deterministicExecutiveDayBrief | POST /api/workflow-runs | workflow_runs artifact.renderedBrief | Code inventoried | Partial passed | Manual with model disabled/missing | 2026-06-22 | API integration: workflow produced model-safe/deterministic brief in isolated environment. | Open | P0
PT-058 | Executive Workflow | Risk and leverage detection | As a user, the day brief calls out conflicts, prep gaps, blockers, stale work, due items, waiting-on items, approvals, and schedule pressure. | Risk detection scans calendar/Linear/local context; ranking produces Today’s Three and Highest Leverage Today ordered by urgency/proximity/unblocking/value/energy. | server buildExecutiveCandidates/detectExecutiveRisks | workflow internal | artifact.rankedDayCandidates, risks | Code inventoried; deterministic risk and candidate ranking covered by unit tests | Passed | node:test fixture for executive candidates and risk detection | 2026-06-22 | Passed: fixtures cover calendar conflicts, meeting load, stale/due Linear issues, due commitments, waiting-on commitments, degraded connector diagnostics, day-aware candidate inclusion, and unblocking work ranking above lower-value Linear cleanup. | Open | P0
PT-059 | Executive Workflow | Calendar planning engine | As a user, Pillar Time proposes focus blocks around real calendar constraints. | Free-window logic ignores all-day/nonprimary group events as blocking, applies work hours/buffers, maps categories to candidates, and creates schedule blocks. | server calendarBusyIntervals/calendarFreeWindows/proposedCalendarScheduleFromContext | workflow internal + Google Calendar approval | artifact.proposedCalendarSchedule | Code inventoried; pure planning engine extracted and covered by unit tests | Passed | node:test fixture with all-day, context, primary timed event, meeting buffer, work window, candidate category mapping | 2026-06-22 | Passed: all-day/context events are nonblocking, primary timed events block with buffer, free windows are computed, proposed blocks are generated inside windows, and calendar_conflict candidates are skipped. | Open | P0
PT-060 | Intelligence Workflow | Source fetching and rigorous issue selection | As a user, intelligence mode evaluates successful fetches, clusters evidence, selects 12-18 issues, and exposes degraded coverage. | Fetch collection runs active sources, normalizes items, builds coverage diagnostics/candidateScan/evidencePackets/selectedIssueClusters, and avoids false no-news claims. | server fetchSourceCollection/buildRigorousBriefInputs/selectIssueClusters | POST /api/workflow-runs runType intelligence | normalized_items, workflow artifact | Implemented with rigorous intelligence workflow guardrails | Unit partial passed | node --test tests/intelligenceWorkflow.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover selected issue cluster floors/caps/dedupe, coverage diagnostics for degraded X/Reddit/RSS coverage, candidate filtering warnings, and no-news policy that blocks false quiet claims when coverage is degraded or unselected candidates remain. Live intelligence workflow with real active sources and model wording still pending. | Intelligence selection/diagnostic guardrails covered; live runType=intelligence smoke pending. | P1
PT-061 | Intelligence Workflow | Rendered intelligence brief | As a user, intelligence mode renders an up-to-two-page brief with calendar, executive read, top issues, sections, watchouts, and coverage notes. | Rendered artifact includes onePageBrief/strategicBrief selected issues and diagnostics; Telegram chunking handles longer output. | server synthesizeStrategicBrief/renderOnePageBrief/telegramChunks | POST /api/workflow-runs runType intelligence | workflow_runs artifact | Code inventoried | Not tested | Manual intelligence run with sources |  |  | Open | P2
PT-062 | Scheduling | Scheduled source preflight | As a user, sources can be checked ahead of scheduled brief delivery. | Scheduler determines due key/timezone, runs preflight, records diagnostics/audits, and does not run repeatedly for same key. | server startSourcePreflightScheduler/runSourcePreflight | internal scheduler | workflow/source diagnostics | Code inventoried | Not tested | Clock-controlled backend test needed |  |  | Open | P2
PT-063 | Scheduling | Scheduled brief delivery | As a user, a daily/weekly brief can run and deliver automatically at configured time. | Scheduler respects delivery frequency/day/time/timezone, avoids duplicate same-day runs, generates workflow, sends Telegram if configured. | server startBriefDeliveryScheduler/runScheduledBriefDeliveryIfDue | internal scheduler + Telegram | workflow_runs, telegram settings | Implemented with scheduled delivery decision guardrails | Unit partial passed | node --test tests/briefScheduler.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover configured timezone/day/time parsing, invalid delivery time clamping, exact-minute source preflight, due-key generation, duplicate same-day suppression, readiness gating, and due-and-ready workflow eligibility. Live minute scheduler and real Telegram delivery pending. | Scheduler decision guardrails covered; live scheduled run/Telegram delivery smoke pending. | P1
PT-064 | Telegram | Telegram settings and test | As a user, I can save bot token/chat ID/allowed users and send a test message. | Settings modal saves credentials, test validates/send message, errors appear without losing saved state. | src/main.jsx Settings Telegram; server Telegram routes | PATCH /api/telegram; POST /api/telegram/test | telegram_settings | Implemented with Telegram settings/test guardrails | Unit partial passed | node --test tests/telegramSettings.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover form hydration, allowed-user parsing, PATCH payloads, configured-token preservation, save/test messages and tones, server readiness errors, Telegram test text/response shape, and settings modal Send Test wiring. Live Telegram API send pending. | Telegram settings guardrails covered; live Telegram send smoke pending. | P1
PT-065 | Telegram | Telegram commands | As a user, I can use Telegram commands for brief/approve workflows. | Command endpoint handles supported commands such as /brief and approval commands, checks allowed users, records recent commands, and returns useful text. | server pollTelegramUpdates; /api/telegram/commands | POST /api/telegram/commands; Telegram updates | telegram_settings.recent_commands | Implemented with guardrail fix | Unit partial passed | node --test tests/telegramCommands.test.js plus full npm test; npm run build | 2026-06-22 | Added parser/selection tests for /brief-/review-adjacent command handling, pending-only approval selection, unsupported command responses, and recent command capping. Fixed Telegram approve/reject by id to require status=pending. Live Telegram getUpdates, allowed-user enforcement, and real bot delivery remain manual/integration gaps. | Guardrail fixed; live integration pending | P0
PT-066 | Settings | Model providers | As a user, I can configure OpenAI, Anthropic, OpenRouter, Gemini, or Grok from Settings. | Provider cards reflect active/ready state; modal can detect models, save key/model/base URL where applicable, and switch active provider. | src/main.jsx Settings provider modal; server model routes | PATCH /api/model; POST /api/model/models | model_settings | Code inventoried | Partial passed | Manual each provider failure/success where creds available | 2026-06-22 | Browser smoke: Settings route renders. | Open | P1
PT-067 | Settings | Research connectors | As a user, I can configure X, Google Calendar, Reddit, and Linear connectors from one place. | Connector table reflects connection status and opens proper modal; save/test/disconnect flows update connector diagnostics. | src/main.jsx Settings connector modals; server connector routes | PATCH /api/connectors/:provider plus provider tests | connector_credentials | Implemented with settings connector guardrails | Unit partial passed | node --test tests/settingsConnectors.test.js plus full npm test; npm run build | 2026-06-22 | Extracted and tested Settings research connector table rows, status labels, modal target routing, Google Calendar checkbox selection safety, save/test/disconnect request builders for X/Reddit/Linear/Google Calendar, and diagnostic message tone. Browser modal open/save/test visual smoke and live connector calls remain pending. | Settings connector guardrails covered; browser/live connector smoke pending | P0
PT-068 | Settings | Local dependencies | As a user, I can see and repair local FFmpeg/STT dependency health. | Settings reports FFmpeg and optional Whisper status; FFmpeg install action uses Homebrew; Whisper model download appears only when binary exists. | src/main.jsx Settings local deps; server ffmpeg/stt routes | GET /api/runtime/ffmpeg; GET/POST /api/runtime/stt/model/install | runtime env, data models dir | Implemented with local dependency guardrails and server-side Whisper model gate | Unit partial passed | node --test tests/localDependencies.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover FFmpeg/STT readiness display, Whisper model download visibility only after binary exists, FFmpeg Homebrew install request paths, runtime route request shapes, unsupported/already-installed FFmpeg install decisions, and server-side refusal to download Whisper model without whisper.cpp binary. Live Settings click-through and real install/download actions pending. | Local dependency guardrails covered; live install/download smoke pending. | P1
PT-069 | Settings | ElevenLabs audio setup | As a user, I can save ElevenLabs key/voice/model and preview audio. | Setup can list voices, choose voice, save settings, preview sample, and optionally enable Telegram MP3 auto-send. | src/main.jsx ElevenLabsSetup; server TTS routes | POST /api/tts/voices; PATCH /api/tts; POST /api/tts/preview | tts_settings, connector_credentials.elevenlabs | Implemented with ElevenLabs setup guardrails | Unit partial passed | node --test tests/elevenLabsSetup.test.js; npm test; npm run build | 2026-06-22 | Helper tests cover saved voice hydration, detected voice choice, voice/save/preview request contracts, Telegram auto-send payload, save readiness, setup message tones, ElevenLabs API voice filtering, and TTS settings patch validation for missing key/voice. Live ElevenLabs API, browser playback, and Telegram MP3 delivery pending. | ElevenLabs setup guardrails covered; live API/preview/Telegram audio smoke pending. | P1
PT-070 | Settings | Audit log visibility | As a user, I can see recent state-changing actions. | Audit table shows timestamp/actor/action/entity/note for last entries and empty state otherwise. | src/main.jsx Settings/Audit; server audit() | /api/state | audit_logs | Code inventoried | Not tested | Manual after state changes |  |  | Open | P2
PT-071 | Google Calendar | OAuth and calendar selection | As a user, I can connect Google Calendar, list calendars, choose primary calendars, and disconnect. | OAuth uses PKCE, stores refresh token, list endpoint fetches calendars, selection requires at least one calendar, disconnect disables connector. | server googleCalendar OAuth/list/select/disconnect; Settings modal | POST/GET calendar routes | connector_credentials.google_calendar | Implemented with OAuth selection guardrails | Unit partial passed | node --test tests/googleCalendarOAuth.test.js plus full npm test; npm run build | 2026-06-22 | Extracted and tested deterministic Google Calendar OAuth start plan, PKCE consent URL fields, callback refresh-token persistence, transient OAuth state clearing, calendar-list selection defaults, and selected-calendar validation. Live Google OAuth consent, external Chrome open, and browser modal interaction remain manual/integration gaps. | OAuth/calendar selection guardrails covered; live OAuth/browser smoke pending | P0
PT-072 | Google Calendar | Calendar write permissions | As a user, approved calendar plans should create events only when write scope/credentials are ready. | Write readiness checks connected credential and required scope; create event uses selected write calendar/default primary with extended properties. | server assertGoogleCalendarWriteReady/createGoogleCalendarEvent | Google Calendar events.insert | Google Calendar API | Code inventoried; write readiness and event request guardrails covered by unit tests | Unit partial passed | node:test fixture for write credential scope, writable calendar selection, and event request payload; live Google insert still needed | 2026-06-22 | Unit coverage confirms disconnected credentials fail, missing calendar.events scope requires reconnect, selected writable calendar fallback works, summary/start/end validation fires, and Pillar Time metadata is preserved in event extendedProperties. Live events.insert remains untested. | Open | P0
PT-073 | Runtime | Backend sidecar and app state | As a desktop user, the app backend starts locally, serves state/static app, and can shut down for replacement. | Tauri bundles node backend sidecar, backend serves /api/state and dist, runtime shutdown exits cleanly for newer backend. | scripts/prepare-tauri-sidecar.mjs; server static/runtime routes; tauri.conf | GET /api/state; POST /api/runtime/shutdown | local SQLite, dist resources | Code inventoried | Build passed | Packaged app launch smoke | 2026-06-22 | Vite production build passed; packaged app launch still needs desktop smoke. | Open | P0
PT-074 | Runtime | Optional Whisper packaging | As a user, desktop builds do not carry Whisper unless I install/configure it separately. | Release bundle includes only pillar-time-backend external bin; no vendor/whisper tracked; UI explains optional local install; model download depends on binary availability. | tauri.conf.json; scripts/prepare-tauri-sidecar.mjs; Settings; docs | GET /api/runtime/stt | WHISPER_* env/data models | Code inventoried | Verified package partial | DMG find no whisper + manual STT status | 2026-06-22 |  | Open | P0
PT-075 | Release | Apple Silicon notarized DMG | As an Apple Silicon user, I can download and install a notarized DMG from GitHub. | DMG is signed, notarized, stapled, Gatekeeper-accepted, and uploaded to public release. | release artifact + prior command output | GitHub release asset | Pillar.Time_0.1.3_aarch64.dmg | Verified current artifact | Passed | stapler/spctl/hash/upload verified | 2026-06-22 |  | Closed | P0
PT-076 | Release | Apple Intel notarized DMG | As an Intel Mac user, I can download and install a notarized x64 DMG from GitHub. | x64 app and backend binaries are x86_64, DMG is signed/notarized/stapled/Gatekeeper accepted, uploaded to public release. | release artifact + prior command output | GitHub release asset | Pillar.Time_0.1.3_x64.dmg | Verified current artifact | Passed | stapler/spctl/file/hash/upload verified | 2026-06-22 |  | Closed | P0
PT-077 | Data / Migration | SQLite migration and seeding | As a user upgrading from earlier builds, local data migrates and defaults seed without duplicate destructive resets. | Migration creates/updates required tables, backs up pre-Pillar Time migration, seeds source/time/trusted-context defaults idempotently. | server migrate/seedSourceRecord/seedTimeDefaults/seedTrustedContextDefaults | startup migration | SQLite database | Code inventoried | Partial passed | Fresh DB + migrated DB smoke | 2026-06-22 | API smoke: isolated DB migrated/seeded; /api/state returned 165 sources and 9 reviews. | Open | P0
PT-078 | Security / Privacy | Credential posture | As a user, secrets are stored only where intended and env-only connectors do not leak keys. | Model/X/Reddit/Telegram/ElevenLabs credentials store masked status; Linear key stays environment-only; UI placeholders never echo saved secrets. | server credential helpers; Settings connector UI | connector settings routes | connector_credentials, env vars | Implemented with public credential views | Unit partial passed | node --test tests/credentialPosture.test.js plus full npm test; npm run build | 2026-06-22 | Extracted and tested public credential state serialization for stored-key connectors, Telegram, Reddit OAuth, Google Calendar OAuth, Linear env-only posture, and model settings. Tests use fake secrets and assert serialized API views do not echo them. Settings placeholders were code-inspected but still need browser visual smoke across modals. | Credential view tests added; browser placeholder smoke pending | P0

## Summary
Metric | Value
Canonical tracker created | 2026-06-22
Total feature/user stories | 78
Passed/verified rows | 20
Open rows | 58
Priority P0 rows | 35
Next phase | Continue testing every user story and documenting errors in this workbook
Automated baseline | npm test passed 206/207 with 1 opt-in Linear smoke skip; npm run build passed on 2026-06-22
Browser smoke baseline | Post-onboarding Playwright smoke partially passed for core routes, Planner task/date, Sources modal, and Reminder master switch on 2026-06-22.
Partial passed rows | 10
Not tested rows | 4
API integration baseline | Core local API CRUD/validation and executive_day workflow passed on isolated localhost 41991 on 2026-06-22.
Unit partial passed rows | 44
Build passed rows | 1
Verified package partial rows | 1
Total stories | 78
Feature status counts | Code inventoried: 32, Code inventoried; approval-gated Linear executor guardrails covered by unit tests: 1, Code inventoried; backend calendar blocking invariant covered: 1, Code inventoried; backend proposal block generation covered: 1, Code inventoried; calendar schedule approval executor guardrails covered by unit tests: 1, Code inventoried; deterministic risk and candidate ranking covered by unit tests: 1, Code inventoried; model provider validation and discovery parsing covered by unit tests: 1, Code inventoried; profile fact validation and hydration covered by unit tests: 1, Code inventoried; pure planning engine extracted and covered by unit tests: 1, Code inventoried; queue serialization and approve/reject transition rules covered by unit tests: 1, Code inventoried; regeneration context normalization and synthesis payload covered by unit tests: 1, Code inventoried; scheduler decision logic covered by unit tests: 1, Code inventoried; write readiness and event request guardrails covered by unit tests: 1, Implemented with ElevenLabs setup guardrails: 1, Implemented with OAuth selection guardrails: 1, Implemented with RSS source form and feed parsing guardrails: 1, Implemented with Reddit OAuth/API and fallback guardrails: 1, Implemented with Telegram pairing guardrails: 1, Implemented with Telegram settings/test guardrails: 1, Implemented with Today reminder preview guardrails: 1, Implemented with UX wording fix: 1, Implemented with X quick-search guardrails: 1, Implemented with YouTube source feed guardrails: 1, Implemented with agenda timeline helper guardrails: 1, Implemented with audio brief generation/playback guardrails: 1, Implemented with brief setup draft fallback guardrails: 1, Implemented with constitution view and versioning guardrails: 1, Implemented with desktop update view-state guardrails: 1, Implemented with guardrail fix: 1, Implemented with local dependency guardrails and server-side Whisper model gate: 1, Implemented with onboarding completion guardrails: 1, Implemented with onboarding flow guardrails: 1, Implemented with perspective lens generation guardrails: 1, Implemented with perspective lens management guardrails: 1, Implemented with podcast source and transcription gating guardrails: 1, Implemented with public credential views: 1, Implemented with quick task capture guardrails: 1, Implemented with reminder default guardrails: 1, Implemented with review template guardrails: 1, Implemented with rigorous intelligence workflow guardrails: 1, Implemented with scheduled delivery decision guardrails: 1, Implemented with settings connector guardrails: 1, Implemented with source suggestion selection guardrails: 1, Implemented with starter commitment guardrails: 1, Implemented with web source fetch guardrails: 1, Verified current artifact: 2
Test status counts | Build passed: 1, Not tested: 4, Partial passed: 10, Passed: 18, Unit partial passed: 44, Verified package partial: 1
Priority counts | P0: 35, P1: 30, P2: 13
Last updated | 2026-06-22

## Test Log
Run ID | Date | Story ID | Tester | Environment | Steps Performed | Expected | Actual | Result | Evidence Path / URL | Issue ID | Retest Result
AUTO-20260622-001 | 2026-06-22 | PT-014, PT-028, PT-030, PT-042, PT-043, PT-044 | Codex | Local repo node test runner | Ran npm test | 20 node:test cases execute with no failures; live Linear smoke may skip when RUN_LINEAR_SMOKE unset | 19 passed, 1 skipped, 0 failed | Passed | terminal: npm test
AUTO-20260622-002 | 2026-06-22 | PT-073 | Codex | Local repo Vite production build | Ran npm run build | Production frontend compiles without errors | Vite build passed; dist assets generated | Passed | terminal: npm run build
BROWSER-20260622-001 | 2026-06-22 | PT-001, PT-003, PT-013, PT-019, PT-022, PT-026, PT-027, PT-028, PT-032, PT-043, PT-050, PT-066 | Codex | Playwright Chromium against isolated localhost:41991 | Loaded fresh app before onboarding complete and tried direct hashes | Onboarding should gate incomplete setup; direct feature routes require completed onboarding | Onboarding gate appeared for most routes; treated as test precondition, not product bug | Passed with note | local Playwright output in Codex turn
BROWSER-20260622-002 | 2026-06-22 | PT-013, PT-019, PT-021, PT-022, PT-026, PT-027, PT-028, PT-032, PT-043, PT-050, PT-066 | Codex | Playwright Chromium after completing onboarding in isolated DB | Visited main routes, created Planner task/date, opened source modal, toggled reminder master switch | Routes render expected pages; basic no-credential interactions persist state | Routes rendered; task/date persisted; source modal opened; visible reminder switch changed API state | Partial passed | local Playwright output in Codex turn
API-20260622-003 | 2026-06-22 | PT-013, PT-014, PT-015, PT-019, PT-020, PT-021, PT-022, PT-023, PT-024, PT-026, PT-027, PT-028, PT-030, PT-032, PT-045, PT-046, PT-056, PT-057 | Codex | Isolated localhost:41991 API with temp SQLite | Called core local CRUD/validation endpoints and executive_day workflow with wait=true | All endpoints accept valid payloads, reject required invalid payloads, and return refreshed state/artifact | All checked endpoints passed; executive workflow completed with recognizable brief text | Passed | local API integration output in Codex turn
UNIT-20260622-004 | 2026-06-22 | PT-039, PT-051, PT-059 | Codex | Local repo node:test runner | Ran node --check server/index.js, npm test including tests/executivePlanning.test.js, and npm run build | Calendar planning logic is syntactically valid, automated tests pass, and production frontend still builds | node --check passed; npm test passed 23, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Passed | terminal: node --check server/index.js; npm test; npm run build
UNIT-20260622-005 | 2026-06-22 | PT-058 | Codex | Local repo node:test runner | Extracted deterministic executive candidate/risk analysis to server/executivePlanning.js; ran npm test and npm run build | Executive analysis detects risks and ranks day candidates without live credentials; production frontend still builds | npm test passed 25, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Passed | terminal: npm test; npm run build
UNIT-20260622-006 | 2026-06-22 | PT-072 | Codex | Local repo node:test runner | Extracted Google Calendar write guardrails to server/googleCalendarWrite.js; ran npm test and npm run build | Write readiness, selected calendar fallback, event payload metadata, and validation errors are deterministic and tested without live Google API access | npm test passed 28, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-007 | 2026-06-22 | PT-049, PT-052 | Codex | Local repo node:test runner | Extracted approval executor to server/approvalExecutor.js; ran npm test and npm run build | Generated Linear/calendar actions cannot execute before approval; malformed unsupported actions fail before connector writes; approved fake connector actions produce expected result/audit payloads | npm test passed 33, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-008 | 2026-06-22 | PT-048 | Codex | Local repo node:test runner | Extracted approval queue transition/serialization helper to server/approvalQueue.js; ran npm test and npm run build | Approval queue list data and approve/reject state transitions are deterministic, validation rejects invalid statuses, and pending selection is stable | npm test passed 36, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-009 | 2026-06-22 | PT-053 | Codex | Local repo node:test runner | Added executiveRegenerationContext/executiveSynthesisPayload coverage; ran npm test and npm run build | Typed/voice missing context is preserved into executive_day regeneration payload and tied to basedOnRunId | npm test passed 37, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-010 | 2026-06-22 | PT-007 | Codex | Local repo node:test runner | Extracted model setup helpers to server/modelConfig.js; fixed empty model parsing; ran npm test and npm run build | Model provider setup decisions are deterministic, credentials are not exposed in state, and bad/empty discovery records do not become selectable models | npm test passed 43, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-011 | 2026-06-22 | PT-025 | Codex | Local repo node:test runner | Extracted scheduler decisions to server/reminderScheduler.js; ran npm test and npm run build | Reminder scheduler gates, due-time detection, dedupe, and delivery channel planning are deterministic and covered without live Telegram | npm test passed 48, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-012 | 2026-06-22 | PT-029 | Codex | Local repo node:test runner | Extracted profile fact normalization/hydration helpers in server/trustedContext.js; ran npm test and npm run build | Profile fact creation rules validate required fieldKey, apply safe defaults, preserve trust/visibility metadata, and hydrate stored rows safely | npm test passed 50, skipped 1 opt-in Linear smoke, failed 0; npm run build passed | Unit partial passed | terminal: npm test; npm run build
UNIT-20260622-014 | 2026-06-22 | PT-065 | Codex | Local macOS dev checkout | Added tests/telegramCommands.test.js; ran node --check on server/index.js, server/telegramCommands.js, and tests/telegramCommands.test.js; ran npm test; ran npm run build. | Telegram command parsing is deterministic; approval selection cannot target non-pending items; unavailable commands are explicit; recent command history caps at 20; full suite and frontend build pass. | node --check passed. npm test: 55 tests, 54 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | server/telegramCommands.js; tests/telegramCommands.test.js; server/index.js; terminal output 2026-06-22 |  | Unit partial passed; live Telegram bot command flow remains untested.
UNIT-20260622-015 | 2026-06-22 | PT-047 | Codex | Local macOS dev checkout | Added src/progressViewModel.js and tests/progressViewModel.test.js; wired GeneratingBrief to the view model; ran node --check, npm test, and npm run build. | Progress screen derives current step, completed/error status, slow-step class, exact error text, and done-state progress deterministically; no duplicated punctuation in running status messages. | node --check passed. npm test: 59 tests, 58 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/progressViewModel.js; tests/progressViewModel.test.js; src/main.jsx; terminal output 2026-06-22 | ERR-20260622-PT047-001 | Unit partial passed; browser visual smoke remains pending.
UNIT-20260622-016 | 2026-06-22 | PT-078 | Codex | Local macOS dev checkout | Added server/credentialPosture.js and tests/credentialPosture.test.js; wired production state serialization through public credential views; ran node --check, npm test, and npm run build. | Serialized public state reports saved/configured/env credential status without returning raw Model/X/Reddit/Telegram/ElevenLabs/Google Calendar/Linear secrets; Linear remains environment-only. | node --check passed. npm test: 63 tests, 62 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | server/credentialPosture.js; tests/credentialPosture.test.js; server/index.js; terminal output 2026-06-22 |  | Unit partial passed; browser placeholder smoke remains pending.
UNIT-20260622-017 | 2026-06-22 | PT-071 | Codex | Local macOS dev checkout | Added server/googleCalendarOAuth.js and tests/googleCalendarOAuth.test.js; wired OAuth start/callback/list/select routes through the helper; ran node --check, npm test, and npm run build. | OAuth start uses PKCE/offline consent URL fields; callback stores refresh token and clears oauthState/codeVerifier; list endpoint keeps explicit selection or falls back to primary/selected calendars; calendar selection requires at least one calendar. | node --check passed. npm test: 68 tests, 67 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | server/googleCalendarOAuth.js; tests/googleCalendarOAuth.test.js; server/index.js; terminal output 2026-06-22 |  | Unit partial passed; live Google OAuth and browser modal smoke remain pending.
UNIT-20260622-018 | 2026-06-22 | PT-010 | Codex | Local macOS dev checkout | Added src/calendarOnboarding.js and tests/calendarOnboarding.test.js; wired the onboarding calendar step to the helper; ran node --check for helper/test, npm test, and npm run build. | Calendar onboarding starts OAuth, refreshes local state, opens returned authUrl externally, refreshes calendars when connected, tests connector when disconnected, and renders success/warning tone correctly. | node --check passed for src/calendarOnboarding.js and tests/calendarOnboarding.test.js. npm test: 72 tests, 71 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. Direct node --check on src/main.jsx is not applicable because Node does not load .jsx without Vite/Babel. | Passed | src/calendarOnboarding.js; tests/calendarOnboarding.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; live Google OAuth callback and browser visual smoke remain pending.
UNIT-20260622-019 | 2026-06-22 | PT-067 | Codex | Local macOS dev checkout | Added src/settingsConnectors.js and tests/settingsConnectors.test.js; wired Settings research connector table/actions to the helper; ran node --check, npm test, and npm run build. | Connector table reflects X, Google Calendar, Reddit, Linear, Web Search, and YouTube status; editable rows route to proper modals; save/test/disconnect request builders target expected APIs; Google Calendar selection cannot remove the last selected calendar; failure messages render as warnings. | node --check passed. npm test: 77 tests, 76 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/settingsConnectors.js; tests/settingsConnectors.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser modal and live connector smoke remain pending.
UNIT-20260622-020 | 2026-06-22 | PT-004 | Codex | Local macOS dev checkout | Added src/starterCommitment.js and tests/starterCommitment.test.js; wired onboarding addStarterCommitment through helper; ran focused test, npm test, and npm run build. | Submitting starter commitment creates both a quick onboarding task and daily commitment, caps Today’s Three rank, clears input on success, refreshes state, and reports warning without side effects for blank input. | node --test tests/starterCommitment.test.js passed 5/5. npm test: 82 tests, 81 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/starterCommitment.js; tests/starterCommitment.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser onboarding smoke remains pending.
UNIT-20260622-021 | 2026-06-22 | PT-005 | Codex | Local macOS dev checkout | Added src/reminderDefaults.js and tests/reminderDefaults.test.js; wired onboarding reminder switches through helper; ran focused test, npm test, and npm run build. | Reminder master/channel defaults save only to time preferences; channel defaults merge safely; individual reminders remain controlled by explicit reminder switches. | node --test tests/reminderDefaults.test.js passed 4/4. npm test: 86 tests, 85 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/reminderDefaults.js; tests/reminderDefaults.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser onboarding smoke remains pending.
UNIT-20260622-022 | 2026-06-22 | PT-006 | Codex | Local macOS dev checkout | Added src/reviewTemplates.js and tests/reviewTemplates.test.js; wired onboarding review toggles through helper; ran focused test, npm test, and npm run build. | Review template toggle updates enabled state, shows confirmation, reports failures, and does not send scheduling/reminder prompt fields directly. | node --test tests/reviewTemplates.test.js passed 5/5. npm test: 91 tests, 90 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/reviewTemplates.js; tests/reviewTemplates.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser onboarding smoke remains pending.
UNIT-20260622-023 | 2026-06-22 | PT-008 | Codex | Local macOS dev checkout | Added src/briefSetupDraft.js and tests/briefSetupDraft.test.js; wired onboarding brief draft/apply through helper and broadened local fallback to model/key/provider failures; ran focused test, npm test, and npm run build. | Brief setup draft uses canonical API when available, local fallback on route/model failures, preserves user intent/preferences, supports editable sections, and applies through canonical endpoint or compatible fallback writes. | node --test tests/briefSetupDraft.test.js passed 4/4. npm test: 95 tests, 94 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/briefSetupDraft.js; tests/briefSetupDraft.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser onboarding smoke remains pending.
UNIT-20260622-024 | 2026-06-22 | PT-009 | Codex | Local macOS dev checkout | Added src/sourceSuggestions.js and tests/sourceSuggestions.test.js; wired onboarding source selection/access/skip/save through helper; ran focused test, npm test, and npm run build. | Source suggestions preserve selected set, identify blocked prerequisites, route blocked selections through setup, let users skip blocked source classes, and save only ready selected sources. | node --test tests/sourceSuggestions.test.js passed 5/5. npm test: 100 tests, 99 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/sourceSuggestions.js; tests/sourceSuggestions.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser onboarding source UI smoke remains pending.
UNIT-20260622-025 | 2026-06-22 | PT-011 | Codex | Local macOS dev checkout | Added src/telegramPairing.js and tests/telegramPairing.test.js; wired TelegramPairingFlow through helper; ran focused test, npm test, and npm run build. | Telegram onboarding validates token before starting pairing, creates session/QR via pairing endpoint, polls session status, treats paired session or saved enabled settings as connected, and shows clear waiting/failed/connected UI state. | node --test tests/telegramPairing.test.js passed 5/5. npm test: 105 tests, 104 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/telegramPairing.js; tests/telegramPairing.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; live Telegram Bot API smoke remains pending.
UNIT-20260622-026 | 2026-06-22 | PT-012 | Codex | Local macOS dev checkout | Added src/onboardingCompletion.js and tests/onboardingCompletion.test.js; wired Onboarding readiness/save/complete through helper; ran focused test, npm test, and npm run build. | Onboarding completion requires ownerName and scheduleSet, delivery schedule saves through brief config, complete calls server-side completion gate, and completed onboarding reopens at missing required setup if needed. | node --test tests/onboardingCompletion.test.js passed 5/5. npm test: 110 tests, 109 passed, 1 skipped opt-in Linear smoke, 0 failed. npm run build passed with Vite production output. | Passed | src/onboardingCompletion.js; tests/onboardingCompletion.test.js; src/main.jsx; terminal output 2026-06-22 |  | Unit partial passed; browser onboarding completion smoke remains pending.
UNIT-20260622-027 | 2026-06-22 | PT-016 | Codex | Local unit tests and Vite build | Ran node --test tests/quickTaskCapture.test.js, npm test, and npm run build. | Quick task capture rejects blanks, trims title, saves source quick-capture, clears only after persistence success, and preserves input on persistence failure. | Focused tests passed 4/4. Full npm test passed 113/114 with 1 opt-in Linear smoke skip. npm run build passed. | Unit partial passed | tests/quickTaskCapture.test.js; src/quickTaskCapture.js; src/main.jsx Today addTask |  | Browser Today form smoke pending
UNIT-20260622-028 | 2026-06-22 | PT-017 | Codex | Local unit tests and Vite build | Ran node --test tests/todayAgenda.test.js, npm test, and npm run build. | Today timeline uses the latest completed run agenda, falls back to legacy calendar fetch events, shows up to eight events, and preserves calendar URLs for Open buttons. | Focused tests passed 4/4. Full npm test passed 117/118 with 1 opt-in Linear smoke skip. npm run build passed. | Unit partial passed | tests/todayAgenda.test.js; src/todayAgenda.js; src/main.jsx Today timeline |  | Browser Today timeline smoke pending
UNIT-20260622-029 | 2026-06-22 | PT-031 | Codex | Local unit tests and Vite build | Ran node --test tests/constitutionVersioning.test.js, npm test, and npm run build. | Trusted Context shows the current constitution version/body, and constitution updates create the next version with editor/reason and audit metadata. | Focused tests passed 3/3. Full npm test passed 120/121 with 1 opt-in Linear smoke skip. npm run build passed. | Unit partial passed | tests/constitutionVersioning.test.js; src/trustedContextConstitution.js; server/constitutionVersioning.js; server/index.js /api/trusted-context/constitution |  | Browser Trusted Context panel and live DB route smoke pending
UNIT-20260622-030 | 2026-06-22 | PT-033 | Codex | Local unit tests and Vite build | Ran node --test tests/rssSource.test.js, npm test, and npm run build. | RSS modal collects feed URL/keywords and saves locator/config; RSS fetch planning parses RSS/Atom entries, filters today items, and records fetch/cache diagnostics. | Focused tests passed 7/7. Full npm test passed 127/128 with 1 opt-in Linear smoke skip. npm run build passed. | Unit partial passed | tests/rssSource.test.js; src/sourceForm.js; server/rssSource.js; src/main.jsx Sources submit; server/index.js fetchRssSource |  | Browser add-source and live RSS fetch smoke pending
UNIT-20260622-031 | 2026-06-22 | PT-035 | Codex | Local unit tests and Vite build | Ran node --test tests/xSource.test.js, npm test, and npm run build. | X source requires a bearer-token connector; quick search excludes replies/retweets, caps posts, normalizes today posts, estimates cost, and records diagnostics. | Focused tests passed 6/6. Full npm test passed 133/134 with 1 opt-in Linear smoke skip. npm run build passed. | Unit partial passed | tests/xSource.test.js; server/xSource.js; server/index.js fetchXSource; src/sourceForm.js X source definition |  | Live X API and browser source-modal smoke pending
UNIT-20260622-032 | 2026-06-22 | PT-036 | Codex | Local unit tests and Vite build | Ran node --test tests/redditSource.test.js, npm test, and npm run build. | Reddit connector stores client settings, plans OAuth token refresh, constructs source URLs, normalizes subreddit JSON posts, falls back to RSS on 403/429, and records fetch-mode diagnostics. | Focused tests passed 5/5. Full npm test passed 138/139 with 1 opt-in Linear smoke skip. npm run build passed. | Unit partial passed | tests/redditSource.test.js; server/redditSource.js; server/index.js redditCredential/fetchRedditSource |  | Live Reddit OAuth/API and browser connector smoke pending
UNIT-20260622-033 | 2026-06-22 | PT-038 | Codex | Local repo node test runner and Vite production build | Added focused podcast helper guardrail tests; ran node --test tests/podcastSource.test.js; ran npm test; ran npm run build. | Podcast source behavior has deterministic coverage for Spotify resolver patching, transcription gating, RSS audio episode parsing, today/latest selection, no-episode bookkeeping, and duplicate transcript results; full test suite and production build remain green. | Focused podcast tests passed 7/7; npm test passed 145/146 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/podcastSource.test.js; src/podcastSource.js; server/podcastSource.js; npm test output 2026-06-22 |  | Pending live Spotify/iTunes resolver, source modal, and real audio transcription smoke.
UNIT-20260622-034 | 2026-06-22 | PT-054 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused audio brief guardrail tests; ran node --test tests/briefAudio.test.js; ran npm test; ran npm run build. | Audio brief behavior has deterministic coverage for TTS readiness button state, generated/cached MP3 artifact flow, safe /api/audio serving, playback event state, restart reset, and TTS text cleanup. | Focused audio tests passed 6/6; npm test passed 166/167 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/briefAudio.test.js; src/briefAudio.js; server/briefAudio.js; npm test output 2026-06-22 |  | Pending live ElevenLabs generation/playback browser smoke.
UNIT-20260622-035 | 2026-06-22 | PT-063 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused scheduled delivery guardrail tests; ran node --test tests/briefScheduler.test.js; ran npm test; ran npm run build. | Scheduler respects frequency/day/time/timezone, exact preflight minute, duplicate same-day suppression, readiness gating, and due-and-ready workflow eligibility. | Focused scheduler tests passed 6/6; npm test passed 166/167 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/briefScheduler.test.js; server/briefScheduler.js; npm test output 2026-06-22 |  | Pending live minute scheduler and real Telegram delivery smoke.
UNIT-20260622-036 | 2026-06-22 | PT-064 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused Telegram settings/test guardrail tests; ran node --test tests/telegramSettings.test.js; ran npm test; ran npm run build. | Telegram settings save/test behavior preserves saved credentials, validates missing token/chat ID, shapes test message responses, and surfaces success/error messages without losing saved state. | Focused Telegram settings tests passed 4/4; npm test passed 166/167 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/telegramSettings.test.js; src/telegramSettings.js; server/telegramSettings.js; npm test output 2026-06-22 |  | Pending live Telegram API send smoke.
UNIT-20260622-037 | 2026-06-22 | PT-068 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused local dependency guardrail tests; ran node --test tests/localDependencies.test.js; ran npm test; ran npm run build. | Settings reports FFmpeg/STT readiness, routes check/install actions correctly, only shows Whisper model download after binary exists, and server refuses model download without whisper.cpp binary. | Focused local dependency tests passed 5/5; npm test passed 166/167 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/localDependencies.test.js; src/localDependencies.js; server/localDependencies.js; npm test output 2026-06-22 |  | Pending live Settings click-through and real Homebrew/Whisper install smoke.
UNIT-20260622-038 | 2026-06-22 | PT-060 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused intelligence workflow guardrail tests; ran node --test tests/intelligenceWorkflow.test.js; ran npm test; ran npm run build. | Rigorous intelligence flow has deterministic coverage for issue cluster selection floors/caps, coverage diagnostics, candidate warnings, and no-news claim policy. | Focused intelligence tests passed 4/4; npm test passed 184/185 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/intelligenceWorkflow.test.js; server/intelligenceWorkflow.js; npm test output 2026-06-22 |  | Pending live runType=intelligence workflow with real sources and model wording review.
UNIT-20260622-039 | 2026-06-22 | PT-069 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused ElevenLabs setup guardrail tests; ran node --test tests/elevenLabsSetup.test.js; ran npm test; ran npm run build. | ElevenLabs setup has deterministic coverage for voice list normalization, save/preview request contracts, voice selection, Telegram auto-send payload, and missing key/voice validation. | Focused ElevenLabs tests passed 5/5; npm test passed 184/185 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/elevenLabsSetup.test.js; src/elevenLabsSetup.js; server/ttsSettings.js; npm test output 2026-06-22 |  | Pending live ElevenLabs API, preview playback, and Telegram MP3 smoke.
UNIT-20260622-040 | 2026-06-22 | PT-002 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused desktop update guardrail tests; ran node --test tests/desktopUpdates.test.js; ran npm test; ran npm run build. | Desktop update UI state has deterministic coverage for startup checks, available/current/error states, install progress, Help menu, banner, and Settings labels/actions. | Focused desktop update tests passed 5/5; npm test passed 184/185 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/desktopUpdates.test.js; src/desktopUpdates.js; npm test output 2026-06-22 |  | Pending packaged Tauri updater release/install/relaunch smoke.
UNIT-20260622-041 | 2026-06-22 | PT-018 | Codex + 4-worker parallel slice review | Local repo node test runner and Vite production build | Added focused Today reminder preview guardrail tests; ran node --test tests/todayReminders.test.js; ran npm test; ran npm run build. | Today reminder preview has deterministic coverage for first-six rows, next occurrence copy, On/Off badges, edit route, and fallback row data. | Focused Today reminder tests passed 4/4; npm test passed 184/185 with 1 opt-in Linear smoke skip; npm run build passed. | Unit partial passed | tests/todayReminders.test.js; src/todayReminders.js; npm test output 2026-06-22 |  | Pending browser visual smoke against live /api/state.
UNIT-20260622-042 | 2026-06-22 | PT-034 | Codex | Local macOS app repo / Node test runner | node --test tests/webSource.test.js; npm test; npm run build | Feature-specific guardrail behavior passes and app build remains green. | Web source form, request planning, metadata extraction, normalized item, cache/error config all passed; full suite 206/207 with Linear smoke skipped; build passed. | Passed | tests/webSource.test.js |  | Not yet live-smoked
UNIT-20260622-043 | 2026-06-22 | PT-037 | Codex | Local macOS app repo / Node test runner | node --test tests/youtubeSource.test.js; npm test; npm run build | Feature-specific guardrail behavior passes and app build remains green. | YouTube source channel/playlist/search form behavior, feed URL planning, handle resolution, Atom parse, today filtering, and next config passed; full suite 206/207 with Linear smoke skipped; build passed. | Passed | tests/youtubeSource.test.js |  | Not yet live-smoked
UNIT-20260622-044 | 2026-06-22 | PT-040 | Codex | Local macOS app repo / Node test runner | node --test tests/perspectiveLenses.test.js; npm test; npm run build | Feature-specific guardrail behavior passes and app build remains green. | Perspective lens management helpers for edit/add/update/remove/filter, save payload, message tone, and enabled count passed; full suite 206/207 with Linear smoke skipped; build passed. | Passed | tests/perspectiveLenses.test.js |  | Not yet live-smoked
UNIT-20260622-045 | 2026-06-22 | PT-041 | Codex | Local macOS app repo / Node test runner | node --test tests/perspectiveLensGeneration.test.js; npm test; npm run build | Feature-specific guardrail behavior passes and app build remains green. | Perspective lens generation helpers for prompt count inference, backend prompt, draft sanitation, frontend request/success/failure, and voice transcript fallback passed; full suite 206/207 with Linear smoke skipped; build passed. | Passed | tests/perspectiveLensGeneration.test.js |  | Not yet live-smoked

## Errors and Fixes
Issue ID | Story ID | Severity | Title | Observed Behavior | Expected Behavior | Repro Steps | Likely Cause | Fix Commit | Status | Retest Evidence
ERR-20260622-PT047-001 | PT-047 | Low | Progress running status could duplicate punctuation | A step output ending in punctuation, such as Working..., rendered with an added trailing period as Working.... | Running progress text should not add a second sentence terminator when the output already ends with punctuation. | Use a running workflow step whose output is Working... and render the generation progress message. | GeneratingBrief always appended a period after current.output. | Pending commit Add workflow progress view model tests | Fixed | tests/progressViewModel.test.js verifies Step 2 of 3: Working...